## Sheet1
Date | Activity Done | Performed by
2016-10-24 | Project announced
2016-10-25 | Decided Project partner | Tasleem, Rahul
2016-10-26
2016-10-27
2016-10-28
2016-10-29 | Discussion on design of project and how to approach the requirements given | Tasleem, Rahul
2016-10-30 | basic stensil of data structures created | Tasleem
2016-10-31
2016-11-01 | file input read and break into token for handeling | Rahul
2016-11-02 | added logic for passing the instructions into basic 5 stage pipeline | Tasleem, Rahul
2016-11-03 | regression testing on making sure that the instgructions pass thru all the stages | Tasleem, Rahul
2016-11-04 | added logic to handle arithmetic operations | Tasleem, Rahul
2016-11-05 | testing of code up till now | Tasleem, Rahul
2016-11-06 | added logic for branching for jump | Tasleem, Rahul
2016-11-07 | added logic for branching for BAL BZ BNZ | Tasleem, Rahul
2016-11-08 | regression testing for changes made in code till now | Tasleem, Rahul
2016-11-09 | regression testing for input file 1 uploaded. Code not working as expected, so debugging and testing | Tasleem, Rahul
2016-11-10 | regression testing for changes made in code till now | Tasleem, Rahul
2016-11-11
2016-11-12
2016-11-13
2016-11-14 | Added logic for multiple exec stages | Tasleem, Rahul
2016-11-15 | regression testing on multiple stages logic | Tasleem, Rahul
2016-11-16 | added logic for multiple exec stages | Tasleem, Rahul
2016-11-17
2016-11-18 | Bought CD for project submission. Added logic for handeling dependnecies on registers | Tasleem, Rahul
2016-11-19 | Final check and Documentation Preparation. | Tasleem, Rahul